## Slide 1
FIIB PGDM CAPSTONE | PROJECT MANAGEMENT | LEARNING TEAM 6
Wakefit North India (Delhi NCR)
Offline Retail Expansion
A Hub-and-Spoke Rollout Strategy — Final PMO Review (M6)
Wakefit went public in December 2025 to fund a pan-India expansion to 117 stores by FY28. Delhi NCR — its densest northern cluster, next to the company's only North India factory — is the natural hub for expansion into Rajasthan, Uttar Pradesh, Punjab and Himachal Pradesh, just as IKEA's own NCR rollout narrows the competitive window.
The Decision In what order should Wakefit open its 20–25 new NCR-region stores, before IKEA's incoming large-format stores close the window? Delhi NCR is the supply hub, not a rollout target — new stores go to its 4 spoke markets. This project uses WBS, scheduling, PERT/CPM and risk management to answer that sequencing question.
₹1,288.89 Cr
IPO raised, Dec 2025
117 stores
Pan-India target, FY27–28
20–25 stores
NCR region's proportional share
4 spoke markets
Jaipur · Lucknow · Punjab · HP
Team: Chandni Choudhary (PM) · Ankesh Kumar (Operations) · Juhi Varshney (Marketing) · Mayank Jain (Finance)

## Slide 2
1
MARKET ASSESSMENT · WHICH SPOKE, AND WHY
Market Opportunity & Competitive Risk
Spoke Market Priority — from the NCR / Sonipat Hub
1
Jaipur
Existing
Practical road connectivity; strongest near-term fit
2
Lucknow
Existing
Strong market potential; needs longer replenishment planning
3
Punjab / Mohali
Existing
Attractive, but needs assessment beyond Mohali city
4
Himachal Pradesh
Greenfield
Selective approach — terrain & delivery economics are harder
EXISTING WAKEFIT FOOTPRINT
~20 stores
already open in the Delhi NCR hub itself. Spokes add their own separate base — Jaipur (2), Lucknow (3), Mohali (5) — vs. zero in Himachal Pradesh.
Insight: for Jaipur/Lucknow/Mohali this is about deepening network density, not first-time market entry.
!
COMPETITIVE TRIGGER — IKEA
Gurugram opens 2026 · Noida opens 2028
IKEA's entry raises the stakes inside the NCR hub itself — reinforcing why Wakefit's incremental growth is being sequenced outward into the spoke markets, on a disciplined, prioritised timeline rather than blanket simultaneous entry.
Source: Wakefit RHP (IIFL/IDBI Capital, Groww); RoC filings (Entrackr); IKEA/Ingka timelines (Business Standard); Wakefit store locator, Aug 2026.
M6 — Final PMO Review

## Slide 3
2
OPERATING MODEL · HOW WE OPEN & SUPPLY EACH STORE
Operating Model & Rollout Sequence
Site-Selection Workflow — not market size alone
Market
potential
Customer
catchment
Accessibility
Competition
Logistics
feasibility
Cost
POD / INHP Logistics Concept
Sonipat is confirmed as the hub node (Wakefit's only North India factory). What still needs validation are its operating parameters as a distribution hub — warehouse capacity, transport cost, inventory policy and service levels.
20–25 Store Phased Roadmap
Finalised for M6
Working planning estimate, not a confirmed Wakefit regional commitment — presented as a plan still needing validation.
Hub-First Spoke Sequence
NCR / SONIPAT HUB
↓
1 Jaipur
↓
2 Lucknow
↓
3 Punjab / Mohali
↓
4 Himachal Pradesh
Owner: Ankesh Kumar (Operations Head) — rollout framework, POD/INHP logistics, spoke sequencing, PERT/CPM network.
M6 — Final PMO Review

## Slide 4
3
FINANCIAL FEASIBILITY · CAN WE TRUST THE NUMBERS BEHIND THIS
Cost, Risk & Feasibility
Project Engagement Budget — ₹1,32,000
Chart: 
| Professional Fees | Site Visits & Research | Market/Industry Data | Documentation & Reporting | Tools & Software | Contingency (~7%)
Budget | 100000 | 8000 | 5000 | 5000 | 6000 | 8000
Not to be confused with Wakefit's own store investment cost — this is the advisory engagement budget only.
Risk Register — Key Items
FINANCIAL
Conflicting EBITDA/PAT across RHP, RoC & disclosures; FY26 PAT inflated by a ~₹98 Cr one-off deferred-tax gain
OPERATIONAL
North India POD/INHP logistics locations are not publicly disclosed
COMPETITIVE
IKEA's Gurugram (2026) / Noida (2028) timing could shift Wakefit's own sequencing
ESTIMATION
The 20–25 store regional figure is the team's own proportional calculation, not RHP-disclosed
Mitigation: source and definition cited wherever financials are used; conservative assumptions flagged explicitly.
Owner: Mayank Jain (Finance Head) — cost estimation, compliance requirements, risk assessment & mitigation.
M6 — Final PMO Review

## Slide 5
4
SCHEDULING & CHANGE RESPONSE · DID WE STILL DELIVER ON TIME
Schedule, Critical Path & the R-06 Disruption
Critical Path (M4, CPM-confirmed)
0.1
0.2
1.1
1.3
1.4
2.1
2.2
3.1
3.2
3.3
4.4
4.5
Zero float on the full sequence — every activity above is critical. Red = R-06-affected (soft-validated, see below).
R-06
STAKEHOLDER RISK — SCORE 9 (HIGH)
On 1 Sept, sole stakeholder Daljeet Singh became unreachable 2–16 Sept — the exact window WBS 3.2 was due to start, covering all remaining work. His return (16 Sept) falls after the 15 Sept deadline.
Probability: High (3) × Impact: High (3)
3.2 and 4.4 both carry zero float on the CPM calculation — either delay is a day-for-day project delay.
Response — Deadline Held, Findings Flagged
•
1–2 Sept
Asked Daljeet directly for an alternate contact — none existed. Work split into blockers vs. non-blockers.
•
Through 15 Sept
Blockers (3.2, 4.4) proceed on RHP/RoC/press sources with conservative assumptions, each finding individually flagged “provisional.” Deadline unchanged.
•
16 Sept
Validation call with Daljeet on the flagged items only.
•
17–18 Sept
Short addendum updates only the items that changed — the report is not redone.
Owner: Chandni Choudhary (Project Manager) — scheduling, CPM, and the M5 change-scenario response.
M6 — Final PMO Review

## Slide 6
5
CLOSURE
Final Recommendation, Lessons Learned & Closure
FINAL RECOMMENDATION
Sequence the NCR-hub rollout Jaipur → Lucknow → Punjab/Mohali → Himachal Pradesh, prioritising network-density gains in existing markets before the greenfield HP entry.
Time it against IKEA's 2026/2028 NCR entries, and treat the 20–25 store figure as a planning estimate pending Wakefit's own confirmation.
LESSONS LEARNED
A single named stakeholder as the only validation channel is itself a structural risk — R-06 confirmed it in practice, not just on paper.
Future charters for this kind of engagement should name a secondary contact at kickoff, and flag critical-path activities that depend on external input before any disruption occurs.
PROJECT CLOSURE
All M1–M5 deliverables complete. R-06 addendum (if needed) closes 17–18 Sept, after the 16 Sept validation call — outside this project's own deadline.
AI USAGE DECLARATION
AI tools assisted with document structuring, formatting and synthesis of research already gathered by the team. All data sourcing, financial interpretation, scheduling logic and final decisions were performed and reviewed by the team.
Team confirms scope, data sourcing and analysis above; edit the AI Usage Declaration to match your actual submission requirements.
M6 — Final PMO Review